## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Team_Mapping
| Table 1 | Team_Mapping
Sprint-Overview
| Table 1 | Sprint-Overview
Task_Tracking(23-02)
| Table 1 | Task_Tracking(23-02)
Sprint-Overview(Sample)
| Table 1 | Sprint-Overview(Sample)
Task_Tracking(Sample)
| Table 1 | Task_Tracking(Sample)

## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 4 | Thanusri.K | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 4 | Gokul | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Yashwanth | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Suwetha | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Vignesh | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Akash | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 4 | Thanusri.K | DevOps Engineer | Week 2 | No
Batch 1 | Team 4 | Gokul | DevOps Engineer | Week 2 | No
Batch 1 | Team 4 | Yashwanth | DevOps Engineer | Week 2 | No
Batch 1 | Team 4 | Suwetha | DevOps Engineer | Week 2 | No
Batch 1 | Team 4 | Vignesh | DevOps Engineer | Week 2 | Yes
Batch 1 | Team 4 | Akash | DevOps Engineer | Week 2 | No
Batch 1 | Team 4 | Thanusri.K | DevOps Engineer | Week 3 | No
Batch 1 | Team 4 | Gokul | DevOps Engineer | Week 3 | No
Batch 1 | Team 4 | Yashwanth | DevOps Engineer | Week 3 | No
Batch 1 | Team 4 | Suwetha | DevOps Engineer | Week 3 | Yes
Batch 1 | Team 4 | Vignesh | DevOps Engineer | Week 3 | No
Batch 1 | Team 4 | Akash | DevOps Engineer | Week 3 | No

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
1 | Build a strong understanding of cloud computing basics and core cloud platform concepts | 2026-05-06 | 2026-05-07 | Gained foundational knowledge of cloud computing concepts, cloud usage benefits, and key architectural differences between Amazon Web Services and Microsoft Azure.
2 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | 2026-05-08 | 2026-05-09 | Successfully deployed a public virtual machine in Microsoft Azure through both the Azure Portal and Terraform, hosted a basic application, and enabled external internet access.
3 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | 2026-05-11 | 2026-05-12 | Explored and analyzed Microsoft Azure VNet configuration, network architecture components, and Bastion Host implementation for secure connectivity.
4 | Gain a strong understanding of cloud networking fundamentals, including VNet peering and communication between multi-tier applications. | 2026-05-13 | 2026-05-14 | Develop an understanding of the OSI model, Layer 3 and Layer 4 communication, VLAN concepts, routing, NSGs, VNet peering, and transitive peering. Learn how to deploy basic 2-tier and 3-tier applications within virtual networks.
5 | Implement secure cross-account connectivity in Azure using VNet peering architecture. | 2026-05-15 | 2026-05-15 | Develop an understanding of Azure cross-account VNet peering, Microsoft backbone infrastructure, route propagation, gateway transit, and secure private communication between isolated environments. Learn Terraform automation for peering, routing, and security configuration management.
6 | Implement secure hybrid connectivity between Azure and AWS using IPSec VPN tunneling protocols. | 2026-05-16 | 2026-05-16 | Develop an understanding of VPN gateways, IPSec tunnels, IKE Phase 1 and Phase 2 negotiations, encryption mechanisms, and secure Azure-to-AWS hybrid communication using Site-to-Site VPN connectivity architecture.
7 | Implement secure Azure-to-on-premises VPN connectivity using IPSec protocols. | 2026-05-16 | 2026-05-18 | Develop an understanding of Azure-to-on-premises VPN architecture, StrongSwan configuration, IPSec tunnel establishment, routing, firewall rules, and secure hybrid communication between Azure infrastructure and on-premises environments. Learn Terraform automation for the same.
8 | Implement scalable infrastructure with autoscaling capabilities, monitoring solutions, and proactive alerting mechanisms. | 2026-05-18 | 2026-05-19 | Develop an understanding of Azure VM Scale Sets, autoscaling policies, Azure Monitor, alert rules, metric collection, and email notification mechanisms for infrastructure performance monitoring and improved operational visibility.
9 | Understand Azure Application Gateway, WAF, and differences between Layer 4 and Layer 7 load balancers. | 2026-05-20 | 2026-05-21 | Gained knowledge of Microsoft Azure Application Gateway, WAF, and the differences between Layer 4 and Layer 7 load balancers. Understood how request routing, traffic distribution, and application-level security are handled in cloud environments.
10 | Implement host-based and path-based routing using Azure Application Gateway for multiple applications. | 2026-05-21 | 2026-05-22 | Configured and deployed Azure Application Gateway in Microsoft Azure and integrated two backend applications with it. Implemented both host-based and path-based routing rules to forward client requests to the correct applications.
11 | Analyze on-premises Kubernetes cluster challenges and deploy applications on Azure Kubernetes Service using manifests. | 2026-05-25 | 2026-05-26 | Explored the operational challenges and maintenance issues faced in on-premises Kubernetes cluster management and studied the advantages of using Azure Kubernetes Service in Azure. Provisioned an AKS cluster and deployed an application successfully using Kubernetes YAML manifest files

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Thanusri | 5 | Done | Trainer
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Gokul | 5 | Done | Thanusri
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Yashwanth | 5 | Done | Gokul
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Suwetha | 5 | Done | Yashwanth
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Vignesh | 5 | Done | Suwetha
1 | Team4 | T1-001 | Build a strong understanding of cloud computing basics and core cloud platform concepts | Akash | 5 | Done | Vignesh
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Thanusri | 4 | Done | Suwetha
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Gokul | 4 | Done | Vignesh
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Yashwanth | 4 | Done | Gokul
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Vignesh | 4 | Done | Akash
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Akash | 4 | Done | Trainer
2 | Team4 | T1-002 | Understood Azure networking concepts including virtual machine connectivity, DHCP functionality, and public IP assignment. | Suwetha | 4 | Done | Yashwanth
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Gokul | 4 | Done | Akash
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Yashwanth | 4 | Done | Trainer
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Suwetha | 4 | Done | Gokul
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Vignesh | 4 | Done | Yashwanth
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Thanusri | 4 | Done | Suwetha
3 | Team4 | T1-003 | Gained understanding of Azure virtual networking concepts, network architecture design, and secure VM access using Bastion Host. | Akash | 4 | Done | Vignesh
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Gokul | 6 | Done | Trainer
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Yashwanth | 6 | Done | Gokul
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Suwetha | 6 | Done | Akash
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Vignesh | 6 | Done | Suwetha
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Thanusri | 6 | Done | Vignesh
4 | Team4 | T1-004 | Created VNets, subnets, route tables, and NSGs, and implemented VNet and transitive peering. Deployed 2-tier and 3-tier applications, and validated routing, traffic flow, and communication between application tiers using Terraform. | Akash | 6 | Done | Yashwanth
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Gokul | 5 | Done | Vignesh
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Yashwanth | 5 | Done | Thanusri
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Suwetha | 5 | Done | Gokul
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Vignesh | 5 | Done | Trainer
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Thanusri | 5 | Done | Akash
5 | Team4 | T1-005 | Configured Azure subscriptions and cross-account VNet peering. Implemented secure private communication using Microsoft backbone infrastructure, routing, gateway transit, and NSG rules, and validated end-to-end connectivity. | Akash | 5 | Done | Suwetha
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Gokul | 6 | Done | Thanusri
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Yashwanth | 6 | Done | Gokul
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Suwetha | 6 | Done | Trainer
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Vignesh | 6 | Done | Suwetha
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Thanusri | 6 | Done | Akash
6 | Team4 | T1-006 | Configured Azure VPN Gateway and AWS Customer Gateway, and implemented IPSec tunnels, routing, and shared keys. Validated tunnel establishment, packet transmission, and secure hybrid communication between Azure and AWS environments. | Akash | 6 | Done | Vignesh
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Gokul | 8 | Done | Vignesh
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Yashwanth | 8 | Done | Thanusri
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Suwetha | 8 | Done | Gokul
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Vignesh | 8 | Done | Trainer
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Thanusri | 8 | Done | Akash
7 | Team4 | T1-007 | Installed and configured StrongSwan VPN on Linux. Implemented Azure VPN Gateway, IPSec parameters, routing, and firewall rules, and validated tunnel stability, secure communication, and hybrid connectivity troubleshooting activities. | Akash | 8 | Done | Suwetha
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Gokul | 7 | Done | Akash
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Yashwanth | 7 | Done | Trainer
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Suwetha | 7 | Done | Gokul
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Vignesh | 7 | Done | Yashwanth
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Thanusri | 7 | Done | Suwetha
8 | Team4 | T1-008 | Provisioned VM Scale Sets with autoscaling policies and load balancer integration. Configured Azure Monitor, metric alerts, action groups, and email notifications, and performed traffic testing, scaling validation, and Terraform-based monitoring automation. | Akash | 7 | Done | Vignesh
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Thanusri | 5 | Done | Trainer
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Gokul | 5 | Done | Suwetha
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Yashwanth | 5 | Done | Gokul
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Suwetha | 5 | Done | Vignesh
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Akash | 5 | Done | Thanusri
9 | Team4 | T1-009 | Learned secure Azure traffic management using WAF and advanced load balancin | Vignesh | 5 | Done | Yashwanth
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Thanusri | 4 | Done | Akash
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Yashwanth | 4 | Done | Suwetha
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Suwetha | 4 | Done | Tainer
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Thanusri | 4 | Done | Gokul
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Vignesh | 4 | Done | Akash
10 | Team4 | T1-010 | Configured Azure Application Gateway routing for multiple backend application deployments. | Akash | 4 | Done | Yashwanth
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Vignesh | 5 | Done | Trainer
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Akash | 5 | Done | Yashwanth
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Gokul | 5 | Done | Thanusri
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Suwetha | 5 | Done | Gokul
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Thanusri | 5 | Done | Akash
11 | Team4 | T1-011 | Explored AKS deployments and challenges managing on-premises Kubernetes infrastructure | Yashwanth | 5 | Done | Vignesh

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -